{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":6,"n_cols":15,"rows_kept":6,"cut":false,"hidden":false,"merged":[]}
["BUG编号","所属模块","接口","缺陷描述","程度","优先级","测试人","测试时间","负责人","执行人","任务进度%","是否修改","完成时间","回归测试","验证时间"]
["BUG-30","管理中心","/oeis/log/success/page","通过接口导出日志不加限制，导出10万条时，系统停止服务","严重","中","靖松","2025-07-16","孟祥平","孟祥平",100,"是","2025-07-20","已通过","2025-07-21"]
["BUG-31","关联上传","oeis/exam/file/uploadPdfExamFiles","接口上传数据，但数据库缺少“关联时间”","一般","中","靖松","2025-07-16","孟祥平","孟祥平",100,"是","2025-07-20","已通过","2025-07-21"]
["BUG-32","非DICOM协议的影像和/或数据转换为符合DICOM协议的影像和/或数据","DfcRptz","返回的数据中“ImageType”未使用标准英文缩写，而使用的是中文名称","轻微","中","靖松","2025-07-19","孟祥平","孟祥平",100,"是","2025-07-20","已通过","2025-07-21"]
["BUG-33","非DICOM协议的影像和/或数据转换为符合DICOM协议的影像和/或数据","DfcImgz","使用PNG图像进行转换时报10199错误，未能转换成功","一般","中","靖松","2025-07-19","孟祥平","孟祥平",100,"是","2025-07-20","已通过","2025-07-21"]
["BUG-34","非DICOM协议的影像和/或数据转换为符合DICOM协议的影像和/或数据","DfcDatz","转换后的数据中应使用“Image Lateriaty”而不是“Lateriaty”","轻微","中","靖松","2025-07-19","孟祥平","孟祥平",100,"是","2025-07-20","已通过","2025-07-21"]