{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":3,"n_cols":15,"rows_kept":3,"cut":false,"hidden":false,"merged":[]}
["BUG编号","所属模块","接口","缺陷描述","程度","优先级","测试人","测试时间","负责人","执行人","任务进度%","是否修改","完成时间","回归测试","验证时间"]
["BUG-35","检查列表","/oeis/register/item/page","接口返回时不不包含“Success”标识","轻微","中","靖松","2025-07-22","孟祥平","孟祥平",100,"是","2025-07-24","已通过","2025-07-25"]
["BUG-36","管理中心","/oeis/sc/project/saveProject","接口保存数据时，指定关联标准名称时，未能成功写入数据库","一般","中","靖松","2025-07-22","孟祥平","孟祥平",100,"是","2025-07-24","已通过","2025-07-25"]