{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":21,"n_cols":14,"rows_kept":21,"cut":false,"hidden":false,"merged":[]}
["BUG编号","所属模块","缺陷描述","程度","优先级","测试人","测试时间","负责人","执行人","任务进度%","是否修改","完成时间","回归测试","验证时间"]
["BUG-41","界面","主菜单顺序需调整，从上往下： 申请 > 常规 > 特殊","轻微","低","陈喆","2025-08-10","刘灿","刘灿",100,"是","2025-08-14","已通过","2025-08-15"]
["BUG-42","界面","申请登记：在身份证号的生日与出生日期不一致的情况下，点击“保存”按钮，先出来弹窗提示；点击弹窗上的“更新”后，才弹出下图所示的“不一致”信息提示，且此提示文字太小、几秒后就消失了 – 很容易导致忽视了此重要提示","轻微","低","陈喆","2025-08-10","刘灿","刘灿",101,"是","2025-08-14","已通过","2025-08-15"]
["BUG-43","界面","检查列表：患者个人信息顺序从左往右改为：\nPID，患者姓名，姓名拼音，性别，出生日期，年龄；“检查项目结点”、“身份证号” 字段删除","轻微","低","陈喆","2025-08-10","刘灿","刘灿",102,"是","2025-08-14","已通过","2025-08-15"]
["BUG-44","界面","检查列表：1. 在某些检查状态下（即还没有检查结果时），“关联上传”确认按钮应灰掉，不可用\u000b2. 按钮顺序调整为：一、关、临、取\u000b3. 按钮间隔隔开一些\u000b4. “取消检查”的按钮与“临床信息”按钮颜色一致","轻微","低","陈喆","2025-08-10","刘灿","刘灿",103,"是","2025-08-14","已通过","2025-08-15"]
["BUG-45","界面","检查列表：左下角的几个按钮，突出显示“关联上传”按钮","轻微","低","陈喆","2025-08-10","刘灿","刘灿",104,"是","2025-08-14","已通过","2025-08-15"]
["BUG-46","界面","检查列表：“申请信息”按钮及弹窗中的“申请信息”与申请登记的菜单保持一致，改为“临床信息”","轻微","低","陈喆","2025-08-10","刘灿","刘灿",105,"是","2025-08-14","已通过","2025-08-15"]
["BUG-47","界面","常规检查管理：查询条件仅支持通过“PID”查询患者，增加支持“患者姓名”、姓名“首字母”、“门诊号”的查询条件","轻微","低","陈喆","2025-08-11","刘灿","刘灿",106,"是","2025-08-14","已通过","2025-08-15"]
["BUG-48","界面","其他客户端和管理中心各页面的与此类似的提示信息，全部字体加大","轻微","低","陈喆","2025-08-11","刘灿","刘灿",107,"是","2025-08-14","已通过","2025-08-15"]
["BUG-49","界面","常规检查管理：参考微信中的键盘，背景颜色加深","轻微","低","陈喆","2025-08-11","刘灿","刘灿",108,"是","2025-08-14","已通过","2025-08-15"]
["BUG-50","界面","关联上传：“关联上传确认”中的提示文件不通顺，改为：\n提示：点击上方的“关联上传”按钮前，请仔细核算对上述“患者个人信息”、“检查项目”与所关联的“关联影像” / “关联报告”文件的信息是否匹配。增加icon","轻微","低","陈喆","2025-08-11","刘灿","刘灿",109,"是","2025-08-14","已通过","2025-08-15"]
["BUG-51","界面","管理中心：点击“删除” / “编辑” 后，出现弹窗后，背景有行选中效果","轻微","低","陈喆","2025-08-12","刘灿","刘灿",110,"是","2025-08-14","已通过","2025-08-15"]
["BUG-52","界面","管理中心：“编辑”弹窗中，性别“未知”与“不确定”重复。删除“不确定” ","轻微","低","陈喆","2025-08-12","刘灿","刘灿",111,"是","2025-08-14","已通过","2025-08-15"]
["BUG-53","界面","管理中心：列表中的“权限”字段名改为“角色权限”，“数据权限”字段名改为“数据查看权限”","轻微","低","陈喆","2025-08-12","刘灿","刘灿",112,"是","2025-08-14","已通过","2025-08-15"]
["BUG-54","界面","管理中心：“检查类型”>“新增”窗口中,“code”改为“代码”","轻微","低","陈喆","2025-08-12","刘灿","刘灿",113,"是","2025-08-14","已通过","2025-08-15"]
["BUG-55","界面","管理中心：“字典分类”几个字和下面的横线删除","轻微","低","陈喆","2025-08-13","刘灿","刘灿",114,"是","2025-08-14","已通过","2025-08-15"]
["BUG-56","界面","管理中心：“部门字典”1）删除“所属机构”字段\u000b2）“部门名称”字段下的层级增加缩进","轻微","低","陈喆","2025-08-13","刘灿","刘灿",115,"是","2025-08-14","已通过","2025-08-15"]
["BUG-57","界面","管理中心：1. 菜单名修改：“检查项目”、“设备ID”分别改为“检查项目配置”、“设备ID配置”\u000b2. 此两个菜单放到“配置管理”菜单中，从上往下顺序：检查项目配置 – 设备ID配置 – 常规检查配置 – 特殊检查配置 – 检查套餐配置","轻微","低","陈喆","2025-08-13","刘灿","刘灿",116,"是","2025-08-14","已通过","2025-08-15"]
["BUG-58","界面","管理中心：“综合验光”改为“主觉验光”。并同步修改客户端界面","轻微","低","陈喆","2025-08-13","刘灿","刘灿",117,"是","2025-08-14","已通过","2025-08-15"]
["BUG-59","界面","管理中心：“常规检查配置”调整为如下顺序：视力、电脑验光、主觉验光、眼压、焦度计；默认不进行测试，“成功”不展示。配置完成，点击“测试链接”按钮后才显示“成功”或“失败”","轻微","低","陈喆","2025-08-13","刘灿","刘灿",118,"是","2025-08-14","已通过","2025-08-15"]
["BUG-60","界面","管理中心：日志查询：点击“详情”后，弹窗中的“取消”按钮没什么作用。改为“复制”按钮","轻微","低","陈喆","2025-08-13","刘灿","刘灿",118,"是","2025-08-14","已通过","2025-08-15"]